## Description
Change Management Planning Workbook
Plan for change and consider how change will affect stakeholders throughout the project.
Change management involves the people side of change and constitutes a critical process in achieving project outcomes through stakeholder engagement. Planning for change involves clearly defining the business need for change, identifying contributors and obstacles to success, engaging stakeholders and building a coalition of advocates, building communications strategies, anticipating and managing resistance, developing efficient and cost-effective training, and identifying reinforcement strategies to sustain the change. Each of these tabs walks you through the change management activities needed to assist stakeholders through the transition from the existing system to the new one.
Instructions
1. Tab O asks you to consider the overall impact a system migration will have on the people involved (processes, staffing, job roles, etc.). What might present potential obstacles to project success, and what might contribute to the success of the project? 2. Tabs E focus on engaging strategic leaders or influencers and building a coalition of advocates. First, you will identify strategic leaders and influencers. Next, you will build your engagement strategy by identifying key activities through which your coalition of advocates can engage target audiences. 3. Tabs C focus on building a communications plan. First, it is important to identify your communications goals and key messages about the change that will be repeated to various audiences throughout specific timeframes within the project. Once you have identified clear and consistant messaging, begin to build out a communications plan that aligns messaging, timing, mode of communication and target audiance. 4. Tab R allows you to identify and plan for potential difficult or resistant stakeholders who could slow or halt the progress of the project. Because it is impossible to plan for all resistance that might occur during a project, this tool can be used during the "execute" and "monitor and control" phases to help mitigate resistance as it arises. 5. Tabs T will help you build a training strategy based on your approach and needs. We've included these tabs within the Change Managment Planning Workbook because of the stakeholder engagement, communications planning and resistance management that accompany training. Keep in mind that many of the items that you generate here will be used as inputs to the Training Plan Template. You will find these tabs to be more effective if you follow the tabs and activities in a sequential order, starting with "training approach" and ending with "training plan." The tabs encourage moving from a high level vision of success to details related to logistics and materials.
Helpful hints
• Pair this workbook with the Stakeholder Analysis Matrix to identify key stakeholders organizations, groups or individuals prior to completing the tabs in this workbook. • Change management goes hand-in-hand with project management, and these plans should be incorporated into the project plan. • Review the Project Management Framework as you consider the timing of activities across the various phases of the project lifecyle. • Adapt this tool to your needs. You may find you only want to use the communication planning tabs or the training tabs. Consider removing or applying columns or rows to these tabs to collect the information you want to track. • While this workbook is framed in the context of a migration, these worksheets can be adapted for day-to-day operations or other changes your group might be experiencing. • Bolded text (as used above) throughout the workbook indicates that the resource referenced is available elsewhere in the IIS Migration Toolkit.
This resource was developed as part of the Immunization Information System (IIS) Migration Toolkit by PHII in partnership with AIRA and CDC and with financial support from CDC. Last updated June 5, 2019. Questions, comments and suggestions are welcomed at phii.org/iiscontact. | phii.org/migration-toolkit

## O Contributors to success
Contributors to success and potential obstacles
In planning for a system migration, consider the factors that will contribute to the success of the project and those factors that might present obstacles to project success. Map out these opposing factors in their respective boxes below (A and B). Once you have identified the key factors within each category, rank the top three factors from each, and plot those in box C. Consider how you might enhance your contributors to success, and address the potenital obstacles you have identified. As you populate the boxes below, consider how you could successfully utilize your top contributors to mitigate the top potential obstacles you have identified.
A. Contributors to success | C. | Top contributors to success | Top potential obstacles
Ex. |  | 1 | 1
|  | 2 | 2
|  | 3 | 3
B. Potential obstacles
Ex.

## E Strategic leaders
Strategic leaders and influencers
Any successful change involves the strong presence of the project sponsor and influentical leaders. Consider who will make up your coalition of advocates. First, identify the project's sponsor. This is the individual with overall accountability for the project and responsibility for championing the project. Next, identify those individuals within your stakeholder groups who are able to play strategic roles in influencing the progress of the project. Describe the role or roles they will take on within the project and important connections to other strategic influencers within the project. Identify their position on the project. Would you describe these influencers as advocates, neutral or resistors in relation to the project? What do these influencers need to prepare to be strong advocates of the project? Utilize the Stakeholder Analysis Matrix to identify particular individuals within your stakeholder groups who could be particularly influential in the success of your project.
Project sponsor:
Leader/influencer (name) | Organization | Role within organization | Span of influence | Position on project | Level of readiness and outstanding needs
Ex. "

## E Engagement strategy
Leadership engagement strategy
Once strategic leaders and their connections have been identified, draft the statement of what the change is and why there is a need for change. Identify the project phase in which the sponsor or leader will undertake the activity. Identify the target audience and through what event will the influencer reach out (e.g., email, newsletter, staff meeting, outreach, etc). Then outline the specific activities these key individuals can engage in to advance the project. Collect any lessons learned as the activities occur. Be sure to review your business case and adapt messaging to strategic leaders in terms that are meaningful to them. This tool can be used for planning, but will also remain active throughout the project as modifications to the plan may be needed.
What is the change planned?
Why is there a need for change?
Timing (project phase) | Sponsor/leader (name) | Target audience | Event | Activity (actions needed) | Date/time/ frequency | Status | Notes/ lessons learned
E.g., "primary sponsor"

## C Key messages
Communication goals and key messages
Communication is key to keeping stakeholders aware of upcoming changes and reinforcing their participation in activities related to the change. The goals of the communication plan (awareness and reinforcement) are driven through the timeframe stages: short term (next 6 months), intermediate term (7-18 months), and long-term (19-36 months). Define the goals based on timeframe and the message category (core/business need, new IIS functionality, customer support, electronic data exchange, etc.). Draft the key messages you would like the various audience groups to hear. As you work, remember it is important that messages be repeated 5 to 7 times to be understood by the audience. A message may occur throughout all timeframes. Also, consider messaging from the audience's perspective. Are there ways you can address group needs and concerns in your messaging?
Communication goal | Timeframe | Message topic/ category | Key message
Awareness | Short-term | Core/business need | A new and improved Immunization Information System (IIS) is coming called <Name>! It’s not just <the old system name> anymore... We’re implementing a new, user-friendly IIS with many new features. The selected software has already been successfully implemented in <actual number of> states/territories.
Awareness | Intermediate term | Training | We’ll be making training available to help you navigate the new IIS. Plus, we’ll have help desk support available via <email/telephone/url> <days/times>.

## C Communications planning
Communications planning
Create a communications plan using the table below. Identify the project phase within which the communication will be sent (initiate, plan, execute, monitor and control, close). Identify the key strategy the communication will address (raise awareness, educate/train, seek input, update leadership). What topic will the communication address (core/business need, new IIS functionality, customer support, electronic data exchange, training, etc.)? Refer to the "key messages" tab to pull this information and the "message content" that has been developed. Identify the delivery mechanism of the communication (email, IIS message board, meeting, newsletter, online training, onsite training, social media, video, webinar, other). Who will be the sender and receiver of this message? Identify when the communication will be initiated, how frequently it will be shared (daily, weekly, monthly, quarterly, etc.), and when it will be complete. As the project progresses, the status of the communication can be updated. Refer to the project phases illustrated in the Project Management Framework for column A. Refer to the Communications Plan Template for more formal formatting of the information gathered in the "C" tabs.
Timing (project phase) | Key strategy | Message category/topic | Message content (Refer to key messages worksheet) | Delivery mechanism | Sender | Receiver (stakeholder group) | Date to initiate | Frequency | Date to complete | Status
Initiate | Raise Awareness | Core/Business Need | Ex. "A new and improved immunization information system (IIS) is coming called <Name>! It’s not just <the old system name> anymore..." "We’re implementing a new, user-friendly IIS with many new features." "The selected software has already been successfully implemented in <actual number of> states/territories." | Newsletter | IIS Manager | Provider groups |  | Monthly

## R Resistance management
Resistance management planning
Change often induces resistance in people for a variety of reasons. Some project stakeholder groups or individuals may demonstrate resistance as the project rolls out, so it's important to try to anticipate what that may look like to try to address the resistance before it becomes a problem. Begin by identifying potentially resistant stakeholder groups or individuals, then define the resistance by describing what the resistance looks like. Resistance could include emotional, job performance or engagement changes. Brainstorm possible motives for the resistance. This could include a lack of awareness of "what's in it for me (WIIFM)," discomfort with the change in the day-to-day, perceived hardship in adjusting to the change and many other potential motives. Select the method that will be used to identify the resistance (employee feedback, supervisor input, focus group, compliance audit, performance measures, other, etc.). Describe potential mitigation strategies, and assign the person responsible for identifying and responding to the resistance. Refer to the Stakeholder Analysis Matrix to identify individuals or stakeholder groups who may be potentially resistant to the system migration.
Resistant stakeholder group/individual | What does the resistance look like? | Possible motive(s) for resistance | Identification M\method | Mitigation strategies | Resistance manager/ responsible
E.g., "provider group A" |  |  | Employee Feedback

## T Training approach
Training approach worksheet
The training approach outlines your vision of success and high-level project objectives. Answer the questions below to begin building your training approach. Many of the items below will be used as inputs during the training strategy worksheet. The training plan checklist is a good way to track the tasks associated with the training tabs in this workbook. Before beginning, familiarize yourself with your department's business goals, and make sure you have an understanding of your team members' individual role within the department.
Training element | Detail
Objectives | Define a project objective/success:
Q: What is the "business" goal of your training—how will training improve our organization? Focus on action—avoid using "learn" or "know."
A:
Q: How will you measure achievement of the business goal above? Use SMART (specific, measurable, achievable, relevant, time-bound) metrics.
A:
Q: What are the biggest challenges in achieving your business goal above? Categorize the challenges: Are they due to lack of learner knowledge, skills, environment or motivation?
A:
Audience | Perform high-level audience analysis:
Q: Who needs training (of any type) for the business goal to be achieved? Be descriptive and segment as much as needed to build a clear picture of your audience (e.g., include specific job roles).
A:
Q: For each audience segment identified above, how does training that group help your organization achieve its business goal? Do needs differ from group to group?
A:
Q: For each audience segment identified above, ask: What's in it for each group? Are your goals aligned with those of the audience? (It's OK if they're not, but you'll need to consider that.)
A:
Q: For each audience segment identified above, what learning style attributes do they have?
A:
Resources | Perform high-level stakeholder analysis:
Q: Who will be involved in the process of creating and implementing training? Fill out roles and responsibilities for initiating, planning, designing, developing, delivering and evaluating training.
A:
Q: What inputs will we receive from our vendor or other external sources?
A:
Build high-level budget and timeframe:
Q: For each stakeholder listed above, list any potential roadblocks in utilizing them for the training project (time conflicts, resistance to change).
A:
Q: How long should the training project last, from initiation to close?
A:
Q: What major external milestones should we plan toward (e.g., system launch)?
A:
Q: What free or low-cost resources are available to us already (e.g., systems, processes, communication channels, partners)?
A:
Training logistics | Perform environmental scan: What delivery vectors and technology are available to us?
Q: Which training delivery methods best fit the learning styles of our audience, listed above (face-to-face, self-service resources ["job aid"], eLearning, webinars, etc.)?
A:

## T Training strategy
Training strategy worksheet
The training strategy further clarifies and defines training activities, roles, time frame and targeted results. Use this worksheet to build a training strategy based on your approach. Many of the items below will be used as inputs to the training plan worksheet. Consider previous training experiences with your team. Ask yourself what has worked and what has not. Keep an open mind to using different training approaches to deliver your training.
Training element | Detail
Objectives | Build learning objectives
Q: For each audience identified in your approach, list what they must do (not know) for your business goal to be achieved. Be specific (e.g., log in to system, create new record, update record, etc.).
A:
Audience | Build learner personas
Q: Create at least one learner persona and story for each audience identified in your approach. (Identify characterists and goals of each group and write a story: "As a ____, I need to ____ so I can ____.")
A:
Resources | Build a more detailed budget and timeline
Q: What specific phases or activities do you want to move through across the life of your training project? Define milestones for each and identify any methodologies (e.g., ADDIE model).
A:
Q: For the activities above, create a timeline based on which stakeholders will need to be involved. Consider a RASCI chart.
A:
Q: Identify how free or low-cost resources can improve the quality and fit of your training (e.g., pilot participants, known "resistors" willing to give candid feedback).
A:
Training logistics | Develop a delivery strategy:
Q: For each training method identified in your approach, list trade-offs to your organization and project (e.g., LMS will cost $___ but will allow for user tracking and reporting).
A:
Q: For each training method identified in your approach, list trade-offs to the learners. (E.g., does the time commitment of logging into an LMS and taking eLearning fit your physicians' busy schedules?)
A:
Q: Identify opportunities to blend learning (e.g., combine face-to-face shadowing sessions with a handy one-page takeaway guide with a link to more information).
A:

## T Training plan
Training plan worksheet
The training plan outlines specific tasks, milestones, named staff, risks, requirements and metrics. Use this worksheet to build a training plan based on your approach and strategy. It is a good idea to consider the amount of time needed to create a training resource, whether it is a workshop or job aide. This will greatly impact your deliverable timeline. Make sure your stakeholders are on the same page and are available for training plan revisions. Also make the activities outlined in this worksheet actionable by utilizing the training plan checklist or converting to a project schedule. For a more formal presentation of the tasks outlined in this worksheet, complete the Training Plan Template.
Training element | Detail
Objectives | Action map
Q: Create an action map to link your business goal and learning objectives to minimum necessary information:
A:
Audience | Refine the asks to your audiences.
Q: For each audience, create user flows: What is the ask for them across the project lifecycle? How can you communicate value and eliminate waste at every step? Build contingencies for resistance.
A:
Resources | Create a specific training plan.
Q: Are activities staged out and owned by responsible parties?
A:
Q: Has leadership had input into the plan, and do they approve?
A:
Q: What activities may build support or momentum if performed early in the process, in order to get ahead of potential resistance?
A:
Training logistics | Build a training delivery calendar.
Q: When will you... develop training? Pilot training? Hold training events? Communicate to users? Close training? Evaluate training?
A:
Q: Build in time to validate your plan! How are you piloting your training across audience segments?
A:

## T Training plan checklist
Training Plan Checklist
Use this checklist to assign and track progress on identified training activitities. The checklist supplements information and activities captured in the training worksheets and training plan by making items actionable. Enhance this checklist by turning it into a project schedule and adding prioritization to tasks.
Task | Assigned to | Status: (completed, in progress, not started, N/A) | Targeted due date | Notes
Approach
1. Define a project objective/success:
a. The "business" goal of our training is defined as how training will improve our organization.
b. Achievement of the business goal has been measured using SMART (specific, measurable, achievable, relevant, time-bound) metrics.
c. The biggest challenges in achieving our business goal have been categorized, e.g., due to lack of learner knowledge, skills, environment or motivation.
2. Perform high-level audience analysis:
a. Audience segments who will need training (of any type) for our business goal to be achieved have been identified.
b. Audience segments are as specific and descriptive as possible to build a clear picture of our audience (e.g., including specific job roles).
c. Benefits of training each audience segment in helping our organization achieve its business goal have been identified.
d. Training needs that may differ from audience group to group have been identified.
e. Benefits of training for each audience segment have been identified by asking, What's in it for each group?
f. Learner style attributes for each audience segment identified have been defined.
g. Business goals are aligned with those of the audience.
3. Perform high-level stakeholder analysis:
a. High level responsibilities are defined for required roles involved in training.
b. Inputs have been received from our vendor or other external sources.
4. Build high-level budget and timeframe:
m. Any potential roadblocks in utilizing stakeholders for the training project have been identified (e.g., time conflicts, resistance to change).
n. The duration of the training project from initiation to close has been determined and agreed upon.
o. Major external milestones have been identified and planned for (e.g., system launch).
p. Any free or low-cost resources are available for our use (e.g., systems, processes, communication channels, partners).
5. Perform environmental scan:
q. Training delivery methods that best fit the learning styles of our audience have been identified (face-to-face, self-service resources ["job aid"], eLearning, webinars, etc.).
Strategy
6. Build learning objectives:
a. A list has been drafted of what each audience identified in our approach must do (not know) for our business goal to be achieved.
b. The list indicates the specific functions needed by each audience (e.g., log in to system, create new record, update record...).
7. Build learner personas:
c. Personas and user stories have been developed for each audience identified in our approach.
8. Build a more detailed budget and timeline:
d. Specific phases or activities to move through the lifecycle of our training project are identified and agreed.
e. Project methodology and milestones for each project phase have been defined (e.g., ADDIE model).
f. A timeline based on which stakeholders will need to be involved has been created.
g. A RASCI chart has been developed to refine the training project roles and responsibilities.
h. Free or low-cost resources to improve the quality and fit of our training (e.g., pilot participants, known "resistors" willing to give candid feedback) have been identified and retained.
9. Develop a delivery strategy:
i. Trade-offs to our organization and project (e.g., LMS will cost $___ but will allow for user tracking and reporting) for each training method identified in our approach have been identified.
j. Trade-offs to the learners (e.g., time commitment of logging into an LMS and taking eLearning for physicians' busy schedules) for each trainng method identified in our approach have been identified.
k. Opportunities to blend learning (e.g., combine face-to-face shadowing sessions with a handy one-page takeaway guide with a link to more information) have been identified.
Plan
10. Develop action map:
a. An action map to link business goal and learning objectives to required information has been developed.
11. Refine the asks to our audiences:
b. User flows for each audience segment have been created to reflect the ask of them across the project lifecycle.
c. The value and elimination of waste at every step of the project process have been communicated.
d. Contingencies for resistance have been built.
12. Create a specific training plan:
e. Activities are staged out and owned by responsible parties.
f. Leadership has provided input and approved the plan.
g. Activities early in the process to build support or momentum to get ahead of potential resistance have been completed successfully.
13. Build a training delivery calendar:
h. Specific dates to develop training, pilot training, hold training events, communicate to users, close training and evaluate training have been documented and agreed.
i. Sufficient time to validate our plan is available.
j. The plan to pilot our training across audience segments has been documented and agreed.
k. A comprehensive training plan has been documented, vetted and approved for execution.
l. The comprehensive training plan has been communicated to all impacted parties.
m. Any training standard operating procedures (SOPs) have been documented, approved and communicated to all impacted parties.