## Description
Partner Analysis Workbook
Identify key partners and their relationship with the project
Partner analysis constitutes a critical element in aligning key partner expectations with the project's purpose and establishing a common understanding of the project outcomes. Analyzing partners who could impact or be impacted by the project helps inform the communications required to obtain partner agreement with the project strategy and scope. In addition, it identifies the change management activities needed to assist partners through the transition from the existing system to the new one.
Instructions
1. Review the "partner analysis worksheet" tab and modify it to suit your needs. It may not be necessary or feasible to fill out every cell of the worksheet. Critical elements include "partner identification" and "partner interest and influence." Use the additional analysis columns based on your project needs. 2. Brainstorm and identify the partners for your project, both internal and external to your agency. For IIS, these include data suppliers and data users, potential funders, health department leadership and others, such as medical provider organizations (e.g., the state chapter of the American Academy of Pediatrics) who have an interest in your goals. List these partners in the Partner Analysis Worksheet. See the "reference partner list" workbook tab for examples. 3. Assess each partner based on their level of interest and power to influence. The level of interest indicates how readily they could be engaged at an appropriate level in the project, and power to influence indicates the formal or informal power they have to influence the project either positively or negatively. 4. Based on your analysis, add each partner to the "partner analysis matrix" tab in the appropriate cell. Review the "partner communication strategies" tab to understand how partners' interest and influence should drive your communication and engagement strategies. 5. Revisit the "partner analysis worksheet" tab to complete the additional analyses and inform your project planning and execution.
Helpful hints
• Partners can be organizations, groups or individuals, but named representatives from each group or organization should be identified to facilitate direct communications. • Consider completing the partner tools as a project team activity, using Post-It notes to categorize them within a matrix. • It can be challenging to categorize partners into a 2x2/binary matrix. When in doubt, refer to the "partner engagement and communications strategies" tab to determine which strategy might be the best fit to place them within the tool.
This resource was developed as part of the Immunization Information System (IIS) Migration Toolkit by PHII in partnership with AIRA and CDC and with financial support from CDC. Last updated June 27, 2019. Questions, comments and suggestions are welcomed at phii.org/iiscontact. | phii.org/migration-toolkit

## Partner analysis worksheet
Partner analysis worksheet
Partner identification |  |  |  | Interest/influence |  | Additional analysis | [5 empty] | Strategy
Partner/ group/ organization name | Internal or external? | Description | Primary contact person (name, title, contact information) | Interest: What is their level of interest in the project (high, medium, low)? | Influence: How much influence do they have over the project (high, medium, low)? | Are they aware of the project (yes/no)? | Partner's position on project (advocate, neutral, resister) | To what extent does the project impact the partner (from the partner's perspective) (high, medium, low)? | How could the partner benefit from the project? | How could the partner contribute to the project? | How could the partner block/resist the project? | Strategy for engaging the partner | Strategy to receive feedback from the partner (if different from partner engagement)

## Reference partner list
Partner analysis partner list
List of sample IIS partners provided for reference.
Partner/ group/ organization name | Internal or external? | Data submitter? | Data user (query via HL7, look up, and/or run reports) | Description
VFC providers | External | X | X | Providers currently enrolled in the Vaccines for Children program.
Health care providers | External | X | X | Health care facilities where vaccines are administered.
Birthing hospitals/facilities | External | X | X | Facilities where babies are born (hepatitis B vaccine recommended for newborns).
Local public health agencies | External | X | X | Local health department immunization staff.
Pharmacies | External | X | X | Pharmacies where vaccines are administered.
Pediatrician/IIS champion | External |  | X | Individual pediatrician who is an advocate for immunization and IIS.
School nurses | External |  | X | School nurses that need to view immunization records of students enrolled in school to assess compliance with school immunization laws.
State chapter of the American Academy of Pediatrics (AAP) | External |  |  | State chapter of AAP reaches members of pediatric provider community.
EHR vendors | External |  |  | Vendors supporting production or test interfaces between the IIS and provider EHR systems.
Child care providers | External |  | X | Child care centers.
Parents/community members | External |  |  | Parents and community members. Key partners related to consumer access of IIS.
Local immunization coalition | External |  |  | Local advocacy group supporting immunization.
State Chapter of the American Academy of Family Practitioners | External |  |  | Local chapter of the AAFP.
Pharmacy board | External |  |  | Licensing board for pharmacists.
CDC | External |  |  | Provides federal funding to support IIS.
State legislators | External |  |  | Elected officials.
Privacy advocates | External |  |  | Privacy advocates.
Anti-vaccine advocates | External |  |  | Anti-vaccine advocates.
Health insurers | External |  | X | Health plans/insurers (interest in immunization data for HEDIS).
Immunization program manager | Internal |  |  | Immunization program manager.
Immunization program staff | Internal |  |  | Immunization program staff, including staff that support the Vaccines for Children and the Assessment, Feedback, Incentives, and Exchange (AFIX) programs.
IIS staff, including field staff/trainers | Internal |  |  | Staff responsible for supporting the IIS.
Department of health commissioner | Internal |  |  | Commissioner of the state public health agency.
Department of health leadership | Internal |  |  | Bureau and section chiefs/leads, state epidemiologist.
State IT | Internal |  |  | State information technology support staff.
State vital records | Internal |  |  | Vital records program provides birth and death records to the IIS.
State WIC program | Internal |  |  | Program responsible for administering the Women, Infants, and Children (WIC) program.
Medicaid program |  |  |  | State Medicaid.
HIE(s) |  |  |  | State health information exchange (HIE) organization(s).

## Partner analysis matrix
Partner analysis matrix
Power to influence
|  | High | Low
Level of interest | High
Low

## Reference stakeholder communica
Partner analysis: partner engagement and communication strategies
Power to influence
|  | High | Low
Level of interest | High | Strategy: Manage closely. These partners need high levels of ongoing communication and attention to ensure they continue as “high/high.” Think about how you can use them strategically to advance your project. | Strategy: Keep well informed. Provide regular information and status updates.
| Low | Strategy: Increase enagement. Could these partners be used strategically to advance your project? If "yes," do you have a communication strategy to move them to "high influence/high interest"? | Strategy: Keep informed. These are low-priority partners, and you might not need to devote more than maintenance resources to them, i.e., keep them informed.

## Reference strategy options
Partner analysis: example communication strategy options and partner engagement methods
Example communication strategy options
-- Raise Awareness
-- Educate/Train
-- Seek Input
-- Updates to Leadership (or others)
Example partner engagement methods
-- Meetings
-- Advisory Groups
-- Newsletters/Message Board
-- Status Updates
-- FAQs
-- Surveys
-- Requirements Validation
-- Training
-- Testing
-- Conferences

## Definitions
Partner analysis: definitions
Field | Description | Pull down list options | Definition
Level of interest | How readily they could be engaged at an appropriate level in the project. | Low | The project purpose is of minimal interest to the partner.
|  | Medium | The project purpose is of moderate interest to the partner.
|  | High | The project purpose is of high interest to the partner.
Power to influence | The formal or informal power they have to influence the project either positively or negatively. | Low | The partner could exert minimal influence on the project scope, objectives or outcome.
|  | Medium | The partner could exert moderate influence on the project scope, objectives or outcome.
|  | High | The partner could exert significant influence on the project scope, objectives or outcome.
Position regarding project | The partner's position on the project: advocate, neutral, resistor. | Advocate | The partner is a champion of the project scope and objectives.
|  | Neutral | The partner is neither a champion or a resister of the project .
|  | Resister | The partner resists the project scope or objectives.