## Description
Procurement Readiness Assessment
Planning
This matrix serves as a guide for programs to evaluate their own level of preparedness and capacity to begin the procurement process. It also offers a checklist that can allow programs to track progress over the course of the procurement process.
Instructions
1. Begin by reviewing the steps in the attached checklist. 2. Evaluate which steps are already complete and what remains to be done; use this information to evaluate where you are in the procurement process. 3. Use the conclusions from the second step to inform planning for the remainder of the procurement process. 4. Refer to the readiness assessment throughout the remainder of the procurement project to ensure you're on task; use it as a checklist to guide next steps.
Helpful hints
• You don't need to complete the checklist before you begin procurement; simply review the checklist during the planning process before you begin to ensure you understand the steps to come. • The checklist will helps assess where you are as you move through the process. • Don't worry if you are not in progress yet on these steps when you first sit down to evaluate. The purpose of this assessment document is to help you better understand what you've already done and where you need to go next. • The steps outlined in this checklist align with the steps of the procurement toolkit, so this is a useful tool for tracking progress along the procurement process. Refer regularly to this checklist, taking into account the larger context of the more detailed guidance found in the remainder of the toolkit.
This resource was developed by PHII as part of the IIS Procurement Toolkit, in partnership with AIRA and CDC and with financial support from CDC. Last updated Month XX, YYYY. Questions, comments and suggestions are welcomed at phii.org/iiscontact. | phii.org/procurement-toolkit

## Procurement Readiness Checklist
Procurement Readiness Assessment | >Status Options: Completed, In Progress, Not Started, N/A
Task | Status | Notes
Planning
1. Determine the need |  | Exercise: Indicate the activities/tasks completed, in progress or not yet started, and identify 1-3 next steps for the planning phase
a. Materials and artifacts to determine the need to proceed have been researched/reviewed.
b. Business case has been developed to convey the problem(s) to be solved, organizational impacts, as well as the risk(s) of not taking action.
c. Meetings with procurement office contact(s) and partners (e.g., IT, legal) have been scheduled.
d. Mechanism to monitor, track and report on the various activities, tasks and staff needed throughout the procurement process has been established.
e. Mechanism to track key decisions made throughout the procurement process has been created.
f. Required procurement templates, language and materials have been gathered for use.
2. Assemble the team
a. Core team members have been identified and committed to the project.
b. Extended team members within my organization, as well as other agencies and departments, have been identified and committed to the project.
c. Team roles and responsibilities have been assigned.
d. Disciplined project governance has been established for oversight of the procurement progress.
3. Understand available procurement options/timelines
a. Jurisdiction/department limitations/constraints on the project are well understood.
b. Available procurement options to meet our needs, timelines and funding source(s) are well understood.
c. Phases and steps needed to complete the procurement process are well understood.
d. Sufficient lead time needed to complete the procurement process activities is well understood.
e. Sufficient time has been allocated to complete the various activities, including required lead time.
f. The criteria and requirements for a sole source solicitation have been researched, if appropriate.
4. Document requirements
a. Detailed functional, technical and performance requirements documentation is complete and available.
b. Hosting requriements are well understood.
c. Requirements have been prioritized and validated by key stakeholders.
Next steps
Solicitation
5. Craft SOW/PWS/SOO |  | Exercise: Indicate the activities/tasks completed, in progress or not yet started, and identify 1-3 next steps for craft SOW/PWS/SOO phase
a. Required templates, sections and boilerplate language are well understood.
b. Scope and objectives of our procurement are well understood and agreed by all stakeholders.
c. Acceptance criteria of project deliverables are well defined.
d. Specific responsibilities of the jurisdiction and contractor are well defined.
e. Expected procurement outcomes are well understood.
f. Delivery timeline is well defined, understood and agreed.
6. Develop RFP |  | Exercise: Indicate the activities/tasks completed, in progress or not yet started, and identify 1-3 next steps for develop RFP phase
a. Administrative and procedural conditions and rules governing the procurement are well defined and clearly stated.
b. Programmatic descriptions of the deliverables are well defined and clearly stated.
c. Evaluation/scoring method is well defined and clearly stated.
d. Minimum qualifications for bidders are clearly stated within the RFP.
e. Pre-proposal conference scheduled or time period allocated for prospective bidders to ask questions.
f. All pertinent information needed for respondents is included in the RFP.
g. Proposal document checklist is provided to assist bidders in ensuring submission of a complete package.
7. Publish RFP/Solicit Bids |  | Exercise: Indicate the activities/tasks completed, in progress or not yet started, and identify 1-3 next steps for publish and make a selection phases
a. Jurisdiction's restrictions or procedures for posting the RFP are well understood.
b. Jurisdiction's restrictions or procedures for alerting prospective bidders are well understood.
c. Deadline for submission and schedule for responding are clearly stated.
8. Make a selection
a. Due diligence conducted to include use case demonstrations, in-person presentations and referral checks to gauge state/customer satisfaction with prospective contractors.
b. Evaluation team consists of various program staff as well as reviewers from outside the program.
c. Clear instructions are provided to reviewers.
d. A score sheet that matches the evaluation criteria is provided to reviewers.
e. A tone of objectivity and non-bias is established during the review period.
Next steps
Contract
9. Draft contract |  | Exercise: Indicate the activities/tasks completed, in progress or not yet started, and identify 1-3 next steps for draft contract phase
a. Nature of the contract (firm fixed price/time and materials, deliverables-based or hourly, and exclusive or non-exclusive) is clearly stated.
b. Full process for contract creation, review and approval is well understood.
c. Required contract template, boilerplate narrative and language are available.
d. Resources required to draft, negotiate and approve the contract are available.
e. Penalties for non-performance are clearly stated.
f. Service level agreements are stated within the contract.
g. Periodic meetings are scheduled for program and vendor leadership.
10. Negotiate with vendor - Not included in guidance document
11. Execute the contract - Not included in guidance document or workshop
Next steps