## Description
Project Schedule Template
Map out key milestones and tasks to develop a project schedule
A project schedule is a tool that lists all project milestones, activities and deliverables with associated owners and timelines to completion. The schedule is estimated based on resource allocation, budget, task duration and task dependencies. A complete schedule helps to communicate the overall effort and duration of a project. Use this tool to help map out key milestones, tasks and dates to inform the development of a project schedule. There are several tools that are helpful in tracking tasks, automating communications on project status and visualizing the schedule in the form of a Gantt chart. Some examples of such tools include Microsoft Project, Smartsheet and ProofHub.
Instructions
1. Determine the appropriate scheduling tool for your project. 2. Define the columns required to monitor and track specific project milestones, activities and tasks such as ownership, responsibility, start and end dates, dependency, and status. 3. For each project milestone, determine the specific activities and tasks required to achieve the milestone. 4. Complete the columns across for each activity and task to determine the overall time required to achieve the milestone. 5. Indent the activities/tasks beneath the milestone to enable auto scheduling of start/end dates/duration.
Helpful hints
• If the schedule is done in MS Project or another tool that team members do not have access to, routinely export the schedule to Excel and/or PDF for distribution and posting to the project repository for team access and review. • Project schedules should be maintained by the project manager and reviewed in terms of completed and outstanding activities/tasks and risks with the project team and executive sponsors on a periodic basis. • Each task (line item) in the schedule should have an assigned resource. Refer to the RASCI Chart for task assignments. • If using Microsoft Project, enable "Auto Schedule" to determine appropriate start/end dates and roll-up timeframe to complete the listed activities/tasks to acheive a milestone. Also, auto "Update" messages can be added to the status and resource roles to automate progress updates from the team. • Individual activities/tasks should be listed in separate rows in the schedule unless it makes sense to group them. • Milestones can be assigned to an accountable resource with specific underlying activities/tasks assigned to responsible resources.
This resource was developed as part of the Immunization Information System (IIS) Migration Toolkit by PHII in partnership with AIRA and CDC and with financial support from CDC. Last updated July 22, 2019. Questions, comments and suggestions are welcomed at phii.org/iiscontact. | phii.org/migration-toolkit

## Project schedule template
Project schedule template
Sample milestone/task | Duration | Start | Finish | Predecessors | Resources | Status
Project initiation
Project planning
Communications
Requirements
Procurement
Develop RFP
Publish RFP
Vendor selection
Contract execution
Configuration
Testing
Data cleansing
Data migration and validation
Training
Go-live
Post go-live warranty period
Project close-out

## Project schedule-sample
Project schedule: sample |  | 494
Task ID | Task name | Duration (days) | Start | Finish | Predecessors | Resource(s) | Status
0 | Public Health Informatics Project | 494 | 2018-01-01 | 2019-05-10 |  |  | In Progress
1 | Initiate | 60 | 2018-01-01 | 2018-03-02 |  | Steve | In Progress
1.1 | Define project concept | 4 | 2018-01-01 | 2018-01-05 |  | Larry | Complete
1.2 | Conduct due diligence | 11 | 2018-01-08 | 2018-01-19 | 1.1 | Alex, Jamie
1.3 | Develop business case | 11 | 2018-01-22 | 2018-02-02 | 1.2 | Larry
1.4 | Identify stakeholders (internal/external) | 18 | 2018-02-05 | 2018-02-23 | 1.3 |  | Needs Attention
1.5 | Draft charter | 18 | 2018-02-05 | 2018-02-23 | 1.4 | Susan
1.6 | Obtain approval of charter | 4 | 2018-02-26 | 2018-03-02 | 1.5 | Susan, Steve
2 | Plan | 109 | 2018-03-05 | 2018-06-22
2.1 | Schedule and conduct kickoff meeting | 4 | 2018-03-05 | 2018-03-09
2.2 | Define project governance | 11 | 2018-03-05 | 2018-03-16
2.3 | Confirm resources | 39 | 2018-03-05 | 2018-04-13
2.4 | Draft project plan | 11 | 2018-04-16 | 2018-04-27
2.6 | Develop communication plan | 25 | 2018-05-21 | 2018-06-15
2.7 | Establish project repository | 4 | 2018-06-18 | 2018-06-22
3 | Execute | 137 | 2018-04-16 | 2018-08-31
3.1 | Schedule project meetings | 4 | 2018-04-23 | 2018-04-27
3.2 | Execute project management plan | 123 | 2018-04-30 | 2018-08-31
4 | Monitor | 207 | 2018-09-03 | 2019-03-29
4.1 | Determine and track project metrics | 207 | 2018-09-03 | 2019-03-29
4.2 | Track progress toward goals - per project plan | 207 | 2018-09-03 | 2019-03-29
5 | Close | 39 | 2019-04-01 | 2019-05-10
5.1 | Prepare and conduct project post mortem | 11 | 2019-04-01 | 2019-04-12
5.2 | Review deliverables list | 11 | 2019-04-15 | 2019-04-26
5.3 | Post all project artifacts to the project repository | 11 | 2019-04-29 | 2019-05-10
Formulas:
Duration (days) = DAYS([Finish],[Start])

## Definitions
Project schedule: definitions
Field | Definition | Notes
Task ID | Sequential numbering of milestones, activities and tasks.
Task name | Milestone, activity or task to be completed.
Duration | Amount of time from the start date to the end date to complete the milestone, activity or task.
Start | Date task is anticipated to start.
Finish | Date task is anticipated to be complete.
Predecessor | Any dependencies in regard to when a specific milestone, activity or task can begin or end.
Resource(s) | Named resources accountable and/or responsible for completing the milestone, activity or task.
Status | Identifies the stage of, or progress made on, the associated activities or tasks