## Description
RASCI Template
Clarify and assign responsibilities to accomplish project activities and achieve deliverables
A RASCI (responsible accountable support consulted informed) chart organizes a project team across specific project responsibilities and deliverables. It allows for discussion about who will take the lead on a task or deliverable, who will be assigned to collaborate on a task and how that collaboration will work. Individuals, versus groups, should be identified for an activity whenever possible to enhance clarity of assigned roles. The assigned project lead or project manager is typically responsible for building out this worksheet; however, it may be useful to complete together as a project team. It is very important that this worksheet be shared and discussed with the project team for transparency and clarification of roles and responsibilities.
Instructions
1. Identify project tasks and deliverables (activities) your project team must coordinate and/or accomplish. These can be high-level or very detailed project activities based on your needs. 2. For each activity, indicate individuals’ roles: Responsible: The person who will complete the activity. Accountable or approver: The person who is accountable for the results of this activity and/or will approve the activity. Supportive: The person or persons who will assist the responsible person with the activity. This group will assist with much of the actual work. Consulted: The person or persons who provide insight and direction into the activity. They will not do the actual work. Their input is based on their expertise in an area. Informed: The person or persons who need to know the status of the activity. 3. Once the chart is complete, review the final distribution of individuals across tasks to confirm effort is distributed in a way that makes sense and is achievable.
Helpful hints
• Adapt the RASCI template to suit your needs. • It may be helpful to refer to your project plan to build out activities in this template. On the other hand, this workbook may be helpful in assigning individuals to activities within your project plan. • Color-coding consistently listed individuals or groups might ease visualization of the effort distribution. •Another tool that may be used a resource when completing your RASCI is the Project Governance Roles and Responsibilities Worksheet, which outline higher-level roles of individuals and groups involved in the governance of the project.
This resource was developed as part of the Immunization Information System (IIS) Migration Toolkit by PHII in partnership with AIRA and CDC and with financial support from CDC. Last updated May 21, 2019. Questions, comments and suggestions are welcomed at phii.org/iiscontact. | phii.org/migration-toolkit

## RASCI
RASCI
# | Activity | Responsible | Accountable or approver | Supportive | Consulted | Informed

## RASCI Sample
RASCI: sample
# | Activity | Responsible | Accountable or approver | Supportive | Consulted | Informed
1 | (High-level example) Coordinate provider training activities. | Sally | Sally's supervisor | Fred, Anne, Tiffany | PHII, AIRA | Program Manager
2 | (Detailed example) Coordinate workshop and follow-up activities with "provider X." | Sally | Sally's supervisor | Tiffany | N/A | Program Manager
3 | (Detailed example) Coordinate workshop and follow-up activities with "provider Y." | Sally | Sally's supervisor | Fred | N/A | Program Manager

## Definitions
RASCI: definitions
Field | Definition | Notes
# | An identification number for the specific activity/task listed. | May represent an ID from a project charter or other reference document. Or may be used to prioritize tasks, identify categories of tasks, or simply number the RASCI activity list.
Activity | A specific task or activity to be completed.
Responsible | The person who will complete the activity.
Accountable or approver | The person who is accountable for the results of this activity and/or who will approve the activity. | Often the project sponsor.
Supportive | The person or persons who will assist the responsible person with the activity. This group will assist with much of the actual work. | The "supportive" role can be included or excluded based on your project needs. Someone who is heavily involved in the task but does not have as much responsibility as the lead, or person designated as "responsible."
Consulted | The person or persons who provide insight and direction into the activity. They will not do the actual work. Their input is based on their expertise in an area. | You may not need to list anyone in the "consulted" column if it doesn't fit within the project task.
Informed | The person or persons who need to know or should be aware of the status of the activity. | Often a member of leadership or someone outside of the core project team.