## Introduction
Introduction to the Worksheet on IT Services for IIS
This worksheet provides sample information technology (IT) related services that immunization/IIS programs might expect from an IT service provider such as a vendor. A list of "typical" immunization information system (IIS) services is provided, along with a description of each service and possible outputs/deliverables to include in a service level agreement (SLA) or other contractual mechanism. The worksheet is intended to be used by an immunization program as a starting point for identifying and prioritizing service needs and expectations for its IIS. This information was developed primarily as an input to a procurement solicitation and in the negotiation of a SLA or IT contract, focusing on services likely provided by a vendor but potentially by the immunization program (e.g., help desk tier one and training) or central IT (e.g., security assessments).
-- The IIS Requirements Traceability Matrix provides a graphical and narrative description of the functional and nonfunctional requirements for IIS. This worksheet is a companion to the RTM in that it describes IT/vendor services in support of those functional and non-functional requirements.
-- The IIS Migration Toolkit provides extensive guidance related to procuring a new IIS platform or other technology transition. It is based on the five project management lifecycle phases: initiate, plan, execute, monitor and control, and close.
-- The IIS Procurement Toolkit also makes extensive procurement guidance available for IIS-related solicitations.
-- All of these online resources work together to provide comprehensive guidance based on industry best practices.
Contents of the IIS IT Services Worksheet
Guidance | Step-by-step guidance and helpful hints/notes for using the worksheet, typically as part of a procurement process.
Worksheet | Worksheet for jurisdictional review and identification of their IIS platform service needs.
Performance | Specifying financial or other consequences for when contractual service expectations are not met.
Glossary | List of common terms and their definitions.
This worksheet was developed by the Public Health Informatics Institute, in partnership with AIRA and CDC and with financial support from CDC under Cooperative Agreement number 6- NU38OT000316. Learn more at phii.org/iishub.

## Guidance
Guidance for completing the sample IT Services Worksheet for IIS
-- Below are suggested steps and helpful hints when using the IT Services Worksheet as part of a procurement and system development life cycle. -- The services listed within the worksheet tab are provided as sample services and are not intended to be an exact or exhaustive set of IIS services, since each program's needs and resources will vary.
1. Review and understand sample IT services -- Review the sample IT services provided in the Worksheet (columns A - E). -- Research with central IT and/or request vendor's Service Level Agreement (SLA) to see other sample language and other services not listed in the worksheet.
2. Determine the priority of the service (high, medium, low) -- Evaluate the program's priority for the service in column "F". -- An input into priority ranking might include jurisdictional IT standards or policies (may be obtained from your procurement office, legal department or central IT, for example).
3. Determine who will provide the service -- Determine the capacity and capability of program staff; i.e., do you have sufficient number of staff with the appropriate skillset to fulfill specific services internally (e.g., help desk, training, data quality). -- Indicate in column "G" who will provide the service (vendor, central IT or program staff) based on your capacity and capability. -- Indicate in column "H" any specific metrics/deliverables required of the vendor to ensure your service needs are met.
4. Work with your procurement office (and perhaps central IT) to incorporate service expectations and any metrics and deliverables into your solicitation document, new or renewing contract and/or SLA. -- Use the worksheet to inform services and/or service levels to include in the SLA document. -- Identify if a template SLA or other form is required by your jurisdiction (for solicitations) or is provided by your selected vendor (for contracts).
Helpful hints and notes
-- Use the worksheet as a starting point for developing and negotiating a SLA as part of an IIS procurement or contract renewal. Additional services that are specific to your jurisdictional needs can be addressed and added to the worksheet, and services that are not needed can be deleted.
-- While the focus of the services listed in the worksheet are typically provided by a vendor, consider possible roles for the IIS program staff and/or central IT in terms of potentially providing some of the services.
-- Circumstances and priorities may change over time, which could impact which services and/or service support levels are needed.
-- Review security and hosting requirements with central IT to identify any related jurisdictional standards or policies that must be met by a vendor.
-- See the tab on performance for guidance on specifying financial or other consequences for when the vendor does not meet performance standards that were contractually agreed to. Effective communications and contract management can prevent a situation from deteriotating to the point where penalties are required.
-- Refer to PHII's Procurement Toolkit for more information related to solicitation documentation.

## Worksheet
Worksheet: Sample IT Services for IIS
Service name | Service description | Sample outputs/deliverables | Description of outputs/deliverables | Considerations | Jurisdiction priority (H/M/L) | Jurisdiction affordability/capacity | Jurisdiction performance metrics/deliverables
Data cleansing, migration and data validation | The movement of data from legacy system to a new system with a focus on data quality | -- Data cleansing plan in preparation of data migration -- Data migration and validation plan, including a data migration schedule | A data migration plan includes the overall process and schedule for identifying and fixing data quality problems in the current system, mapping and migrating the data through a testing and final migration process, and a final data quality validation process of all data in the new system. | --- Named resources (from program staff, vendor or IT) assigned to complete the data migration tasks by the targeted due date. --- Sufficient time allocated to complete several rounds of data migration extracts/loads as needed to validate data in a new system.
Project management | Services associated with the oversight and management of technical and operational tasks and resources associated with planning and executing an implementation/transition project | -- Project plan -- System configuration documentation -- Implementation/deployment plan | -- Project plan is used to guide both project execution and project control. -- System configuration documentation describes how the system needs to be set up for you as a jurisdiction. This document can be useful in testing, system monitoring, etc. -- Implementation/deployment plan is a comprehensive plan that describes all activities necessary to implement the solution for your jurisdiction. | -- Artifacts should be generated and maintained on a timely basis (recommended project status be updated weekly). -- Even if the vendor is providing project management services, the immunization program will also ideally have project management services available to support the program's obligations/operational plans for system implementation.
System testing | Services associated with performance testing, load testing and security testing to meet all approved requirements | -- System performance test plan -- System test scripts/scenarios -- Maintaining a testing environment -- Testing results report | -- System performance test plan outlines the methods and frequency of ensuring system performance in terms of speed, scalability and stability. -- System test scripts/scenarios describe speed (is it responsive?), scalability (how many simultaneous users can be on?), and stability (is it stable under varying loads?). -- Test results reports provide narrative descriptions and numeric outputs on testing system performance as described above. | --- Availability to review system test results (test evidence) --- Insurance that critical (major) issues resolved prior to user acceptance training (UAT)
Change control | Services associated with documenting, identifying and authorizing changes to an IT environment or to the software | Documented change control process | Written description of the entire workflow for submitting, reviewing, prioritizing and ultimately approving change requests, including clear roles and responsibilities and decision points, either through a change control board or other mechanism. | -- While a part of overall software project management, change control is listed separately here to highlight the importance of being clear on expectations for the process used in requesting, documenting and approving changes to the IT/hosting environment. -- Your selected vendor may have a standard process for change control, but your central IT department may also have a preferred process for all jurisdictional or health department IT projects to adhere to.
Release management | Services associated with planning and executing software deployments | Jointly identify and prioritize jurisdictional enhancements needed to be developed, tested and implemented | Provide release notes (at least one week) in advance of the scheduled release; roadmap to include future delivery items or items to be considered. | While every IIS software customer will have their own release management plan and schedule, there will also be very important dimensions of the vendor's overall software/business strategy and the role of the user community in informing that direction. Working with and through the user group to identify shared/common priorities for enhancements is a critical way to meet your needs and help ensure standardization across users of the system.
User acceptance testing | Software tested by the program (which may include end-users) to ensure the system performs as expected in real-world scenarios, according to specifications outlined in the requirements/configuration documentation | -- User acceptance testing (UAT) plan -- Test scenarios | -- User acceptance testing plan describes the process, methods, test scenarios and expected outcomes for the system user to approve acceptance of system functionality or enhancements. --Test scenarios provide detailed description of real-world situations (who is doing what for what purposes and with what expected outcome) to ensure the system (or new enhancement) is functioning as expected/desired. | --- Leverage existing test scripts/use cases for UAT as a starting point that may include test cases received from the vendor and embellished by the program to include typical scenarios --- Availability of test reporting and resolution management processes and tools --- Understanding of release management process for resolution/deployment of fixes/enhancements
Training | Services associated with training activities and output for implementation/transition that could include train the trainer sessions, end-user training, online training and system documentation provided by the vendor or jurisdiction depending on the system and resources available (funding and staff) | -- Implementation/transition training plan -- End user manual -- Administrator manual -- Training videos, YouTube channel vignettes and other media | -- Implementation/transition training plan is the description of methods, schedules, roles and responsibilities and other aspects of ensuring jurisdictional and end users understand the features and processes for effectively using the new IIS. -- End user manual is the reference guide for using the IIS that end-users can access in order to look up features and procedures, presumably online. -- Administrator manual is the reference guide for the jurisdictional system administrators that provides in-depth descriptions and procedures for all functionality within jurisdictional control/configurability. | -- Review and refine training plan early, ensuring tiered levels of training based on internal staff roles with the IIS. -- Leverage and refine training materials from the vendor and/or materials developed by other jurisdictions using the same IIS product. -- Program can utilize other departments (e.g., communications) or partnerships with universities or not-for-profit organizations to develop interactive or digital training media.
System and network monitoring | Services associated with system monitoring (usage, availability, performance, etc.), security risk monitoring and monitoring the operating environment | -- System monitoring report -- Real-time alerts | -- System monitoring report is a routine output of system usage, availability, performance, security threats/attacks and other factors. This report may come directly from a cloud hosting service (e.g., Microsoft Azure) rather than from the IIS vendor. -- Real-time alerts for notification of system failure. | -- Ensure the report provides data on what is most meaningful to you in terms of system performance. -- In many cases, the IIS vendor is providing the cloud environment, even if they are acquiring it from a cloud hosting service company such as Microsoft, Google or Amazon. Therefore, the IIS vendors are beholden to the cloud hosting service companies for timely reporting/resolution. -- See the IIS Procurement Toolkit guidance on "How many '9s?" for balancing system availability and costs.
Data backup | Ensure that there is a data backup plan and schedule that is being executed as specified. | Backup plan and schedule | -- Backup plan and schedule is a description of the procedures, frequency, backup location, access privileges and other aspects of ensuring a backup copy of the IIS data is securely stored and can be accessed for recovery purposes as needed (see next). -- The backup plan should also include restoration testing, and evidence that the backups are happening per the plan (e.g., that test restores are successful). | Check with central IT and/or the Chief Security Officer for jurisdictional standards related to backup and recovery. Such standards would likely have been specified in the solicitation document and/or the statement of work with the vendor.
Disaster avoidance and recovery management | Recovery or continuation of vital technology infrastructure, systems and data following an adverse security event or disaster | -- Disaster recovery plan, including periodic testing of the plan -- Business continuity plan | -- Disaster recovery plan is a description of the procedures, allowable time frames, roles and responsibilities, and other aspects of returning IIS functionality and data to normal following an adverse security event or disaster (natural or man-made). Similar to the data backup plan, the disaster recovery plan must be exercised and tested to ensure it will work when needed. -- Business continuity plan documents the procedures for continuing IIS operations during a service interruption, e.g., power outage, server crash, natural disaster, etc. | See IIS Functional Standard 6.4, "The IIS establishes backup and recovery plans identifying the required equipment, procedures, and the maximum allowable downtime for recovery from adverse security events and disasters" and related Operational Guidance Statements.
User support/technical assistance | --Provide a centralized resource to respond verbally or in writing to questions, troubleshoot problems/issues and facilitate solutions to known problems (addressing and resolving inquiries or requests). -- Support is usually set up in tiers, with Tier 1 serving as the basic level of support (often referred to as the Help Desk), Tier 2 involving advanced levels of support or specialized expertise and Tier 3 being a rare but critical need for support. | -- User guide -- Frequently asked questions (FAQ) "cheat sheet" -- Online support application | -- A user guide is a readily accessible reference resource for end users (typically online) to refer to for answers to questions on routine functionality and procedures, e.g., how to add a new shipment of vaccine, how to edit a record. -- A FAQ cheat sheet is a quick reference guide that addresses some of the most common information needs of users. | -- Tier 1 support is typically considered for end users, with Tiers 2 and 3 geared to program staff. Depending on the program's available resources and vendor's capability, the tiers of support, as well as the escalation process for providing support, are determined and documented by the program or vendor. -- As questions arise, they can be added to FAQs, system documentation and/or training materials for clarification. -- Ideally, response times from the vendor are negotiated and specified in the SLA or other contractual document. For instance, "Acknowledge critical issues within two hours of being logged, and resolve within four hours." Response times are dependent on how much the issue impacts the function and/or users of the IIS (those noted as critical severely impacting the IIS) and may not necessarily be dependent upon the support tiers.
Incident management | Services related to resolving an identified issue caused by an occurence of an unplanned outage or unplanned event; differs from disaster management in that the issues being resolved are of lower severity and scale than in disasters. | -- Biweekly meetings to discuss outstanding problems/issues -- Issue resolution and escalation management plan -- Corrective action plan -- After action plan | -- Document plan for the identification, reporting and escalation of issues and resolution. -- Communicate the plan to ensure end users are aware of the issue management protocols based upon the severity and frequency of the events. | -- Enable mechanism for bi-directional reporting between end users and the program of issues/resolution. -- Plan should include escalation of issues if not resolved within stated service level agreements. -- Unplanned outages should be communicated to end users to keep them informed of the situation and resolution. -- Follow-up actions to be taken should be documented/assigned to avoid recurrence and mitigate any gaps that could decrease service levels.
Data quality monitoring and improvement | Continuous monitoring of the data and identifying opportunities to enhance data quality | -- Data quality plan -- Data quality reports -- Data quality queries | -- Develop data quality plan to ensure continuous monitoring of both incoming IIS data and data at rest. -- Communicate the plan and methods for improving data quality. | -- The CDC IIS Dashboard Report provide important data quality indicators which can help identify priorities for improvement. Data quality monitoring and improvement includes both incoming data into the IIS as well as data at rest.
|  |  | -- Develop queries to monitor data quality on a continuous basis. | -- The IIS Data Quality Blueprint is another great reference.
HL7 onboarding Services | Vendor services associated with the planning, testing and execution of electronic data exchange of patient and vaccine administration data between the data submitters and the IIS | Sample HL7 onboarding documentation may include: -- Onboarding terms & acronyms -- Roles & responsibilities -- Most current national HL7 Implementation Guide -- Transport layer protocol recommendation specification (SOAP/WSDL) -- Delta HL7 Implementation Guide (if applicable) -- Bi-directional Implementation Guide -- Onboarding readiness checklist -- Query and response readiness checklist Execution of HL7 onboarding will encompass: -- Outreach to data submitters to initiate the onboarding process -- Tracking and monitoring the process steps to ensure timely and efficient progress -- Reporting of any HL7 message issues and support needed to ensure timely resolution | -- HL7 onboarding documentation should be made available to data submitters to enable setup of the organization(s) and to establish its credentials for sending HL7 messages in the test and production environments. -- A tracking tool/database for documenting the staus of each provider org/facility through the onboarding process steps. Data to be collected/tracked may include: organization name, HL7 facility code, onboarding phase, status, registration date, kickoff call date, testing start date (QA), testing completion date (QA), go-live call date, go-live date (production) and legacy data load date completed. | -- Program staffing for HL7 onboarding activities should be managed regardless of additional support received to ensure understanding and maintenance of the standard process. -- The continuous rollout of electronic data exchange with both traditional and nontraditional data submitters has become a crucial and significant effort for epidemic/pandemic response, routine vaccinations and school reporting. -- The testing and quality assurance procedures for onboarding are critical to ensure ongoing high data quality. The jurisiction should have clear documentation of procedures for the entire onboarding process to ensure consistency across staff and over time.
Security penetration testing | Services to validate that the system complies with jurisdictional and program cybersecurity and system security requirements and best practices, and which identify potential vulnerabilities | -- System audits -- Simulations to discover potential vulnerabilities and exposures to unauthorized access | Conduct automated and manual simulations of potential security threats in gaining system access. | -- This service can be performed by a third party to test/validate the effectiveness of actions taken by the primary vendor. -- Often the jurisdiction's IT unit/agency will also do this type of testing per jurisdictional policy. -- Testing can be done in production and/or test environments. -- Often low-risk events can be leveraged together to enable unauthorized access/control.

## Performance
Strategies for ensuring effective performance
When contracting for IT services, the core question is how to ensure the vendor meets, if not exceeds, those service expectations. Effective communication is critical for reinforcing good performance and proactively addressing performance that is concerning. Such communications can include regular check-ins to identify, discuss and resolve issues. Occasionally bringing in more senior staff on both sides can also be a useful way to escalate and resolve any issues that are getting “stuck.” Routine reports from the vendor on performance metrics can enable appropriate monitoring. Incentives can also be provided to encourage performance beyond the agreed-to performance metric. But prudence demands also including penalty clauses in the contract or service level agreement for when, despite all efforts, serious performance problems arise. Such penalty provisions, whether of a financial or other nature, are a tool of last resort to ensure the vendor is meeting contractually agreed-upon performance expectations.
As with the rest of a contract, crystal clear, unambiguous language is extremely important in defining and negotiating penalties. Below are questions to ask yourself as you work with your jurisdictional procurement/contracting staff to craft penalty provisions.
-- Are the services (and any outputs/deliverables) written clearly and concretely enough that it can be objectively determined whether or not the service was provided as agreed to?
-- Are the penalties for not meeting/delivering the service clear? If different penalties relate to different services, is that clearly described?
-- Are the penalties incremental, that is, in increments of severity based on varying levels in terms of contract violations? (Tip: avoid a situation in which the only penalty is contract cancellation.)
-- Are the incremental penalties appropriately aligned with the severity of non-performance? That is, are less severe penalties associated with less consequential instances of non-performance? For example, a jurisdiction could refuse to accept a system release or documentation if the requirements had not been sufficiently addressed.
-- Are program staff informed about how to provide supporting documentation or input related to vendor or central IT failures to meet performance standards?
-- Is a clear process provided for dispute resolution?
-- Is the cancellation/termination clause clear as to if, why, when, by whom and how the contract could be cancelled/terminated by the jurisdiction?
-- Does it include the obligations of the jurisdiction and/or the contractor in case of a cancellation?
To re-emphasize, enacting penalties is a worst case scenario, one to prevent if at all possible. Part of effective contract management is ensuring that any performance issues are addressed early enough that penalties are not needed. The key to prevention is ongoing, effective, objective, clear, two-way communication between you and your vendor team.

## Glossary
Glossary of terms
The terms included below are commonly used in IT services solicitations.
For definitions of general terms related to immunizations, see the CDC Vaccines and Immunizations Glossary.
For definitions of general terms related to IIS, see the AIRA MIROW Common Vocabulary resources.
Term | Definition
Acceptable quality level (AQL) | Defines the level of performance that is deemed satisfactory. May be expressed as a percentage of or as an absolute number (e.g., three per month). Defines a maximum allowable error rate or variation from the standard.
Agile software development | A set of principles, methods and practices that involves developer and user teams collaboratively, iteratively and rapidly defining, developing, testing and deploying new software features or modules. Compare to the traditional waterfall software development approach (see below).
Bugs | An error, fault, mistake or defect that causes an unexpected or erroneous result or output.
Change control board | A governance body composed of immunization program leadership and experts to prioritize IIS system fixes and enhancements in collaboration with the vendor and/or central IT. This body has specific accountability for determining priority across competing program initiatives, and approving funding decisions for enhancements and/or bug fixes.
Deliverable | Tangible artifact developed/maintained that is to be delivered to the jurisdiction.
Defect | Problem with functionality of product, where the system is not functioning as intended. May be critical or non-critical.
Enhancements | Changes to software requested by the jurisdiction to meet specific jurisdictional needs.
Error | A reproducible failure of a system to perform a specified function.
Error levels | Can be defined in the SLA; for example: -- Critical: Total system failure; major component not working; mission critical impact. -- High: A function not working with no workaround available; moderate to severe impact to business function. -- Medium: A system/functional error that can be bypassed/occur outside normal routine; low to moderate impact to business. -- Low: A workaround exists; low impact to business function.
Incident | A problem with a system that causes an unplanned interruption to the service.
Incentives | Financial or other motivating offerings to encourage vendor or software performance that will exceed performance standards. Penalties/remedies and incentives complement each other.
Maintenance | Maintaining software, servers, hosting (if applicable) and/or communications infrastructures.
Penalties | Financial or other consequences of a vendor/contractor not meeting the performance standards that were contractually agreed to. Effective two-way communication is always preferred to identify and resolve issues early. Penalties are always a last resort.
Performance metric | Narrative or quantitative measure of performance, ideally objective and unambiguous as to whether achieved or not.
Performance standard | Narrative summary of the expected service level. Performance indicator (e.g., timeliness, quality, quantity) tied to the performance requirements. Can include such elements as "what, when, where, how many and how well" the work is to be performed.
Performance work statement (PWS) | A document that summarizes the work that needs to be done for a contract, including scope and performance requirements. In some jurisdictions, this is called a Statement of Work (SOW). Your procurement office will tell you which template your jurisdiction uses.
Procurement | The process of finding and agreeing to terms, and acquiring goods, services or works from an external source, often via a competitive bidding process.
Remedies | Procedures that address how to manage performance that does not meet performance standards. Remedies and incentives complement each other.
Service level agreement (SLA) | Negotiated terms in an executed contract specifying agreed-upon services, service levels and metrics by which that service is measured; also defines consequences, remedies or penalties if the agreed-on service level is not met and specifies roles and responsibilities of all parties and other interested entities who may not be parties to the agreement. A documented agreement between a service provider and a customer that identifies both services required and the expected level of service (ITIL). [Source: AIRA]
Service level expectation | A narrative and/or quantitative description of the specific services being contractually agreed to and the associated measures/metrics, typically as defined in the SLA.
Solicitation document | A document that identifies the purchase, purchase requirements and outline of a process each offeror must follow when submitting a formal bid or proposal.
Support | Services being provided in support of people and your program.
Upgrades | Routine improvements to software in terms of improved or new features/functionality.
Waterfall software development | A methodology characterized by fully defining and documenting software requirements upfront which then serve as the basis for software development before the product is delivered to the customer for user acceptance testing. Compare to the more iterative, collaboraive agile software development approach (see above).