## Slide 1: IIS Procurement Webinar Series
Week 2: SOW and Solicitation phase
January 21, 2025
Beth Cox, CDC
Candace Garcia, PHII
Marcey Propp, PHII consultant

## Slide 2: Funding disclosure:
This presentation is supported by cooperative agreement number 6 NH23IP922664-01, funded by the Centers for Disease Control and Prevention (CDC). Its contents are solely the responsibility of the authors and do not necessarily represent the official views of the Centers for Disease Control and Prevention or the Department of Health and Human Services.

## Slide 3: Recap of week 1 and Q&A
The overall procurement process: acquisition planning, solicitation and pre-award/award phases
First four steps of acquisition planning:
Conduct market research - RFI, speak with others in the IIS community and your IIS SME
Develop project budget - can only procure what you can afford
Assemble the acquisition team - may shift over the procurement phases
Requirements collection – can be done prior to solicitation; owned by the IZ program

## Slide 4: Acquisition planning: document SOW/PWS
Solicitation
Acquisition planning
Pre-award/award
Conduct market research
Assemble acquisition team
Develop project budget
Collect requirements
Document SOW/PWS
Develop solicitation document
Publish solicitation/Q&A
Evaluate responses
Negotiate contract
Award contract
Develop evaluation criteria

## Slide 5: Document SOW/PWS: considerations
The centerpiece of a solicitation document
  Performance work statement (PWS), statement of work (SOW) or statement of objectives (SOO)
Documenting your needs as requirements drives what is being solicited
Defines the criteria for acceptance
Defines your responsibilities and those of your contractor
Documenting requirements is your primary responsibility!
  Requires significant attention, thought and time
The key to good documentation is precision and completeness
Recommendation:
Be as specific and clear as possible in terms of your service expectations.

## Slide 6: Which to use?
Statement of objectives (SOO)
  Focuses on overall objectives rather than specific requirements
  Least prescriptive, encouraging maximum flexibility in solution offered
Performance work statement (PWS)
  Description of the requirements with greater emphasis on what is to be done rather than how it is to be done
  Best used when project is well defined but there is some flexibility in how requirements are met by a vendor
Statement of work (SOW)
  Detailed description of what specifically is to be accomplished by the vendor in measurable terms, often stipulating how the work should proceed
  Because the jurisdiction is more prescriptive in how to do the work, it may also bear more responsibility for any project failures

## Slide 7: Putting it all together: the SOW
  Background and need: provides a high-level overview of the context for the procurement, including information on your IIS program.
  Procurement objectives: brief and concrete statement of what you want achieved, including the desired benefits to your program.
  Scope of work: describes the services from the perspective of the bidder; that is, what is it you need the bidder to do, both at a fairly high level and in terms of major activities.
  Technical requirements (primarily for software procurements): defines the functional and non-functional (e.g., security, usability, scalability) requirements for the system.

## Slide 8: Putting it all together: the SOW (cont’d)
  Services to be delivered/contractor performance requirements: specifies the tasks you want the contractor to perform and services to be delivered.
  Hosting requirements: specifies any requirements for hosting the IIS, with vendor or “in the cloud.”
  Schedule: provides the timeframes within which the services and deliverables are provided.
  Reporting: specifies how and when you want the successful bidder to report both progress on the requirements or deliverables and on expenditures.
  Other special considerations
  Attachments/references/appendices

## Slide 9: Document SOW/PWS: considerations
Tool
IT Services Worksheet
Considerations
A key document that should be required in the solicitation
Defines the level of service and terms with your vendor, central IT and/or program
Can impact pricing depending on the level of service and terms required
Included as part of the contract at time of award
Recommendation:
Apply the same principles of precision, clarity and understanding of what’s reasonable/afford-able and realistic.

## Slide 10
What will be your approach to documenting SLAs and managing them?

## Slide 11: Solicitation: develop solicitation document
Acquisition planning
Pre-award/award
Conduct market research
Assemble acquisition team
Develop project budget
Collect requirements
Document SOW/PWS
Evaluate responses
Negotiate contract
Award contract
Solicitation
Develop solicitation document
Publish solicitation/Q&A
Develop evaluation criteria

## Slide 12: Solicitation document: considerations
Solicitation document written by whoever in the jurisdiction has procurement authority; generally, the contracting office.
Should be written keeping both the jurisdiction and the offerors in mind.
Need to be crystal clear about the outcomes you want to achieve.
“Good fences make good neighbors.”
Recommendation:
The clearer and more complete you are in the solicitation document, the fewer issues you are likely to experience as the process unfolds.

## Slide 13: Solicitation methods/types
Public
  Request for proposal (RFP)
  Request for quotation (RFQ)
Types
  Competitive bid
  Selective bid
  Single (sole) source

## Slide 14: Sample sections of the solicitation document
Introductory background on the solicitation
Terms of the agreement
Rules governing the competition
Format of the proposal
How to submit proposals
Selection process/criteria
Process for product demonstrations
Offeror qualifications and references
Any special terms and conditions, often unique to the jurisdiction’s laws or policies

## Slide 15: Helpful hints
Some common mistakes made in procurements include:
  Assuming the selected offeror will perform tasks not specified in the solicitation document.
  Assuming the program will have direct access to the data for data cleansing or other purposes.
  Over-specification of either tasks or timelines by a program.
Recommendation:
Structure the solicitation document in outline format so the various components can be clearly referenced. (“In section III.C.1 you say…”)

## Slide 16: Solicitation: develop evaluation criteria
Acquisition planning
Pre-award/award
Conduct market research
Assemble acquisition team
Develop project budget
Collect requirements
Document SOW/PWS
Evaluate responses
Negotiate contract
Award contract
Solicitation
Develop solicitation document
Publish solicitation/Q&A
Develop evaluation criteria

## Slide 17: Evaluation criteria
Need to determine evaluation criteria and identify evaluation panel.
The most effective evaluation panel includes those with sufficient technical knowledge to evaluate the technical responses and evaluate the associated pricing.
The process is designed to be fair and objective.

## Slide 18: Solicitation: Publish solicitation/Q&A
Acquisition planning
Pre-award/award
Conduct market research
Assemble acquisition team
Develop project budget
Collect requirements
Document SOW/PWS
Evaluate responses
Negotiate contract
Award contract
Solicitation
Develop solicitation document
Publish solicitation/Q&A
Develop evaluation criteria

## Slide 19: Publish the solicitation document
Jurisdiction’s rules governing the publication of the solicitation may include:
  Where it is posted and by whom.
  Whether you can directly notify prospective offerors, etc.
  How questions are vetted and responded to.

## Slide 20: Respond to questions
Pre-proposal conference
  Establish a clear process for documenting, formally responding and promptly publishing or sending responses to the questions asked verbally.
  Schedule early enough in the process to be helpful.
  Establish a clear process for receiving, documenting, drafting/reviewing/approving responses to and promptly publishing or sending responses to written questions.
Different requirements for oral vs. written comments?
Deadline for submission and a schedule for responding clearly stated?

## Slide 21
What lessons have you learned from publishing (jurisdiction) or responding (vendor) to a solicitation and/or going through Q&A?

## Slide 22: Upcoming webinars
January 28, 2025: Pre-award/award phase
Join our next session January 28, 2025.
Send your questions to iis@phii.org.